## Sheet1
ISO/IEC JTC 1/SC 22/OWG V N 0130, Schedule for PDTR Ballot, prepared 11 April 2008
Start Date | Event | Days required | Completed Date
2008-04-14 | Leave meeting with disposition of comments | 0 | 2008-04-14
2008-04-14 | Action items completed | 14 | 2008-04-28
2008-04-28 | Editor revises draft | 14 | 2008-05-12
2008-05-12 | Reviewers check draft | 7 | 2008-05-19
2008-05-19 | Editor revises draft | 7 | 2008-05-26
2008-05-26 | Working group review | 28 | 2008-06-23
2008-06-23 | Secretary consolidates comments | 0 | 2008-06-23
2008-06-23 | Contingency | 7 | 2008-06-30
2008-06-30 | Editors meeting | 7 | 2008-07-07
2008-07-07 | Editor revises draft | 14 | 2008-07-21
2008-07-21 | Reviewers check draft | 7 | 2008-07-28
2008-07-28 | Editor revises draft | 7 | 2008-08-04
2008-08-04 | Send to working group for review | 28 | 2008-09-01
2008-09-01 | Secretary consolidates comments | 0 | 2008-09-01
2008-09-01 | Contingency | 14 | 2008-09-15
2008-09-15 | Review of Pre-meeting mailing | 14 | 2008-09-29
2008-09-29 | Stuttgart meeting | 7 | 2008-10-06
2008-10-06 | Action items completed | 14 | 2008-10-20
2008-10-20 | Editor revises draft | 14 | 2008-11-03
2008-11-03 | Reviewers check draft | 7 | 2008-11-10
2008-11-10 | Editor revises draft | 7 | 2008-11-17
2008-11-17 | PDTR ballot | 126 | 2009-03-23
2009-03-23 | Contingency | 21 | 2009-04-13
2009-04-13 | San Diego meeting | 7 | 2009-04-20
Formulas:
Completed Date = [Start Date]+[Days required]
Completed Date = [Completed Date, row above]+[Days required]
Start Date = [Completed Date, row above]