## Sheet1
ISO/IEC JTC 1/SC 22/WG 23 N 0302
Schedule for the preparation of TR 24772, Edition 2
Prepared by Jim Moore
17 December 2010
Start date | # of Days | End date | Activity or Event
|  | 2010-12-16 | End of meeting #16
2010-12-16 | 97 | 2011-03-23 | Editor prepares revision of base document. Liaisons prepare revision of annexes
2011-03-23 | 2 | 2011-03-25 | Meeting #17. Review revised baseline document and revised annexes
2011-03-25 | 30 | 2011-04-24 | Editor assembles entire document and circulates for review
2011-04-24 | 30 | 2011-05-24 | Detailed review of document by WG 23 participants
2011-05-24 | 0 | 2011-05-24 | DEADLINE FOR SUBMISSION OF WRITTEN COMMENTS
2011-05-24 | 26 | 2011-06-19 | Editor prepares recommended disposition of comments
2011-06-19 | 1 | 2011-06-20 | Meeting #18. Discussion of comments
2011-06-20 | 30 | 2011-07-20 | Editor prepares draft for PDTR ballot
2011-07-20 | 15 | 2011-08-04 | Editor submits draft for ballot and Secretariat begins the ballot
2011-08-04 | 90 | 2011-11-02 | Duration of ballot. Note that Meeting #19 occurs during the ballot
2011-11-02 | 41 | 2011-12-13 | Editor prepares recommended disposition of ballot comments
2011-12-13 | 2 | 2011-12-15 | Meeting #20. Disposition of ballot comments
2011-12-15 | 30 | 2012-01-14 | Editor prepares draft for 2nd PDTR ballot
2012-01-14 | 15 | 2012-01-29 | Editor submits draft for ballot and Secretariat begins the ballot
2012-01-29 | 90 | 2012-04-28 | Duration of ballot. Note that Meeting #21 occurs during the ballot
2012-04-28 | 40 | 2012-06-07 | Editor prepares recommended disposition of ballot comments
2012-06-07 | 2 | 2012-06-09 | Estimated date of Meeting #22. Disposition of comments
2012-06-09 | 30 | 2012-07-09 | Editor prepares draft for DTR ballot
2012-07-09 | 15 | 2012-07-24 | Editor submits draft for ballot and Secretariat begins the ballot
2012-07-24 | 90 | 2012-10-22 | Duration of ballot. Note that Meeting #23 occurs during the ballot
2012-10-22 | 45 | 2012-12-06 | Editor prepares recommended disposition of ballot comments
2012-12-06 | 2 | 2012-12-08 | Estimated date of Meeting #24. Disposition of comments
2012-12-08 | 30 | 2013-01-07 | Editor prepares draft for publication
2013-01-07 | 60 | 2013-03-08 | Editor collaborates with ISO staff editor on final manuscript
2013-03-08 | 60 | 2013-05-07 | TR 24772 Edition 2 is published
Formulas:
Start date = [End date, row above]
End date = [Start date]+B8